## Sheet1
CRESCENTES APP(IOS)
IDENTIFIED BY:RANJITH CV
REPORTED TO: |  | ENVIRONMENT DETAILS: Intel(R) Core(TM) i5-8365U CPU WINDOWS 11 |  |  | DATE:
TEST ID | TEST DESCRIPTION | MODULE | EXPECTED RESULT | ACTUAL RESULT | SEVERITY | STATUS | DEVELOPER STATUS
CT_01 | VERIFY STUDENT CORNER MODULE | STUDENT CORNER | ON CLICKING THE DOCUMENTS,IT SHOULD OPEN IN A NEW TAB OR THE SAME WINDOW | ON CLICKING THE DOCUMENTS, IT DOES NOT OPEN; IT KEEPS LOADING INDEFINITELY | HIGH | NEW
CT_02 | ENSURE NOTICE BOARD MODULE | NOTICE BOARD | THE STUDENT SHOULD BE ABLE TO GET THE NOTICE DETAILS FROM THE NOTICE BOARD | THE STUDENT GETS THE NOTIFICATION DETAILS FROM THE NOTICE BOARD | HIGH | NEW
CT_03 | ENSURE EXAMINATION DATE FIELD | EXAMINATION | EACH EXAMINATION ENTRY SHOULD INCLUDE A CLEARLY VISIBLE AND SELECTABLE EXAM DATE | NO DATE FIELD IS PRESENT FOR ANY EXAM, AND NO SCHEDULED OPTION IS AVAILABLE | HIGH | NEW
CT_04 | VERIFY ARRANGEMENT OF EXAMINATION | EXAMINATION | EXAM TYPES SHOULD BE CLEARLY GROUPED AND LABELED UNDER RELEVANT SECTIONS (E.G., MONTHLY, MID-TERM, YEARLY). THE LAYOUT SHOULD BE CLEAN AND STRUCTURED TO IMPROVE CLARITY AND EASE OF NAVIGATION | NO SECTIONS OR GROUPING CURRENTLY PRESENT, MAKING IT DIFFICULT TO SCAN VISUALLY | MEDIUM | NEW
CT_05 | VERIFY DUPLICATE PROFILE SECTION DISPLAYED ON HOME SCREEN | PROFILE | ONLY ONE PROFILE SECTION SHOULD BE DISPLAYED ON THE HOME SCREEN TO AVOID USER CONFUSION AND MAINTAIN CLEAN LAYOUT | TWO PROFILE SECTONS ARE DISPLAYED,ONE AT TOP WITH THE USERNAME AND IMAGE ,AND ANOTHER PROFILE ICON AT THE BOTTOM OF THE SCREEN,CREATING REDUNDANCY AND POTENTIAL CONFUTION | HIGH | NEW
CT_06 | VERIFY TIMETABLE MODULE | TIMETABLE | THE USER SHOULD BE ABLE SEE ALL WEEKDAY COLUMNS(MONDAY TO FRIDAY)WITHOUT HAVING TO SCROLL OR THERE SHOULD BE A VISIBLE SCROLL INDICATOR TO SHOW THAT MORE DAYS ARE PRESENT ON THE RIGHT SIDE | ONLY MONDAY AND TUESDAY ARE VISIBLE INITIALLY.THE USER MUST MANUALLY SCROLL SIDEWAYS TO SEE WEDNESDAY TO FRIDAY.BUT THERE IS NO VISUAL HINT OR SCROLL INDICATOR | LOW | NEW
CT_07 | VERIFY INCONSISTENT YEAR DATA IN CALENDAR MODULE | CALENDAR | CALENDAR SHOULD UPDATE TO REFLECT THE START MONTH OF THE SELECTED ACADEMIC YEAR | CALENDAR STILL DISPLAYS JUNE 2025, EVEN THOUGH 2021–2022 IS SELECTED | MEDIUM | NEW
CT_08 | VERIFY DUPLICATE ACADEMIC YEARS | CALENDAR | ACADEMIC YEAR DROPDOWN SHOULD CONTAIN UNIQUE ENTRIES ONLY | DROPDOWN CONTAINS DUPLICATE ENTRIES FOR ACADEMIC YEAR 2024-2025 | MEDIUM | NEW
CT_09 | VERIFY PAYMENT FUNCTIONALITY | FEE DETAILS | WHEN USER CLICKS ON PAY,SHOULD NAVIGATE TO A PAYMENT GATEWAY OR PAYMENT SCREEN TO COMPLETE THE TRANSACTION | IT SHOWS HOW MUCH IS PENDING,WHEN USER CLICKS PAY,NO ACTION TAKES PLACE,NOTHING HAPPENS.AND USER IS NOT NAVIGATED TO PAYMENT GATEWAY OR NEXT PAGE | HIGH | NEW
CT_10 | VERIFY ENTRIES DELETED FROM SOFTWARE NOT REFLECTED IN APPLICATION | EXAMINATION NOTICE BOARD NOTIFICATION | ONCE AN ENTRY IS DELETED FROM THE SOFTWARE, IT SHOULD BE IMMEDIATELY REMOVED OR HIDDEN IN THE CONNECTED APPLICATION | ENTRY IS STILL VISIBLE IN THE MAIN APPLICATION EVEN AFTER BEING DELETED FROM THE SOFTWARE | MEDIUM | NEW
CT_11 | VERIFY HOMEWORK MODULE | HOMEWORK(NOT PRESENT IN APP) | THERE SHOULD BE A HOMEWORK MODULE OR SECTION IN THE APP WHERE STUDENTS CAN VIEW ASSIGNED HOMEWORKS | THE HOMEWORK MODULE IS NOT PRESENT IN THE APPLICATION. STUDENTS HAVE NO WAY TO VIEW ASSIGNED HOMEWORK | HIGH | NEW
CT_12 | VERIFY SCHOOL BUS MODULE | SCHOOL BUS | THE MAP SHOULD LOAD AND DISPLAY CORRECTLY WHEN CLICKING ON THE GPS/LOCATION ICON | THE MAP FAILS TO LOAD WHEN CLICKING ON THE GPS/LOCATION ICON | MEDIUM | NEW
CT_13 | VERIFY STUDENT ATTENDANCE MODULE | ATTENDANCE | THE STUDENT 'S ATTENDANCE STATUS SHOULD BE DISPLAYED IN THE APPLICATION AFTER BEING MARKED IN THE SOFTWARE | "NO RESULTS FOUND" IS DISPLAYED IN THE APPLCATION EVEN AFTER ATTENDANCE IS MARKED | MEDIUM | NEW
CT_14 | VERIFY VEDIOS SECTION IN STUDENT CORNER | STUDENT CORNER | THE VEDIOS SECTION SHOULD DISPLAY THE AVAILABLE VEDIOS OR SHOW A CLEAR MESSAGE SUCH AS "NO VEDIOS FOUND",IF NONE ARE PRESENT | THE VEDIOS SECTION KEEPS LOADING CONTINUOUSLY WITHOUT DISPLAYING ANY VEDIOS OR A "NO VEDIOS FOUND" MESSAGE | MEDIUM | NEW
CT_15 | VERIFY APPLY LEAVE FUNCTIONALITY | COMMUNICATION | WHEN USER IS TYPING,THE SCREEN SHOULD AUTOMATICALLY SCROLL OR ADJUST TO KEEP THE APPLY LEAVE BUTTON VISIBLE ABOVE THE KEYBOARD | THE APPLY LEAVE BUTTON NOT VISIBLE OR ACCESSIBLE DUE TO ON SCREEN KEYBOARD COVERING IT.USER IS UNABLE TO SUBMIT THE LEAVE REQUEST | MEDIUM | NEW
CT_16 | VERIFY MISSING DUE DATE NOTIFICATION IN FEE DETAILS | FEE DETAILS | DUE DATE NOTIFICATION SHOULD BE SHOWN IF THE FEE IS PENDING | NO DUE DATE NOTIFICATION IS DISPLAYED | LOW | NEW
CT_17 | VERIFY BUS DRIVER CONTACT DETAILS | SCHOOL BUS | DRIVER NAME AND CONTACT NUMBER SHOULD BE SHOWN WITH BUS INFO | NO DRIVER CONTACT DETAILS ARE DISPLAYED | LOW | NEW